## Sheet1
| Open Issues | Status | Priority | Comments
1 | Color coding tests webpage | Complete |  | Added by Thang
2 | Enter correct data into database | Complete |  | Added by Thang
3 | Add chamber chart table for David Seto | Incomplete | Low
4 | Find out how to add modules and their subcomponents to list of DUTs | Incomplete | Moderate
5 | Pairing harnesses with DARs to calculare hours | Incomplete | High | Need to figure out logic
6 | Name for comments on "Tests" and "Chamber Log" webpage need to be decided among "notes", "comments", and "status updates | Incomplete | Low | Need to clarify
7 | Comments on "Tests" page takes from "Chamber Log" page | Incomplete | High
8

## Sheet2
Complete
Incomplete | Low
Moderate
High